## SDP Framework 1
Task | Objectif | Deliverable | Description | Delivery Date | Period | Frequency | Target group | Lead partner | Total Ressources
T.10.1 | Preparation of a dissemination strategy | A10.1 | SDP (Strategic Dissemination Plan) Framework including : | M6
T10.1a | Stakeholders' peer program review, impact assessment and depoyment recommendation | A10.1a | Stakeholders Board for benchmarking measures and impact assessment | M6 |  |  | Partners | W-Smart | (0) 2 | Please give your input in sheets : - "Input Task 10.1" - "Input Task 10.2" - SDP Ressources
T10.1b | Identification of the stakehorders' target groups at the local and European levels | A10.1b | Target Stakeholders’ groups | M6
T10.1c | Determination of the action to be conducted relevant to each stakeholder's target group | A10.1c | Prioritized Actions For each target group at the project or partner levels | M9
T10.1d | Determination of the agenda of major actions | A10.1d | Action Plan and implementation procedure | M9
T10.1e | Reliable and Efficient DSP implemntation management | A10.1e | SDP Implementation - Organizational Management and quality control and updating | M9 | M9-M48 | Each 6M |  |  | (0) 2
T10.2 | Development of dissemination tools and support Objective : - Support online and offline communication of project results and outcomes to target stakeholders | A10.2 | Communication and dissimation tools including : | M1 | M1-M48
T10.2a | Creation of the project graphic identity and communication chart | A10.2a | Communication chart and logo | M1 |  |  | Partners | W-Smart
T.10.2b | Online Communication : Creation of a web-site, blog, newsletter, electronic diffusion lists | D10.1 | Website : Website with project information, project progress information and services | M1 | M1-M48 |  | All stakeholders | W-Smart | 4
|  | D10.2 | Intranet | M1 | M1-M48 |  | Partners | Vitens | (3) 2
|  | D10.3 | Newsletters and other online communication material | M3 | M3-M48 | Each 3 month | Partners and target stakeholders | W-Smart | (14) 8
T.10.2c | Offline Communication : Creation of printed support for the project (flyer, brochure, booklet) | A10.2b | Offline communication material (flyer, brochure, booklet) | M9 | M9-M48 |  | Depending on target objective | W-Smart
T10.2d | Creation of videos/movies on the project challenges and main achievements | A10.2c | Video material | M9 | M9-M48 | M9 ; M24 M36 ; M48 | Depending on target objective | W-Smart
T10.2e | Communication tools to meet partners' needs and requirements | A10.2d | Other communication material will be prepared upon partners' input | To be determined |  |  | Depending on target objective | W-Smart
T10.3 | Dissemination of scientific and innovation outcomes Objectives : - provide scientific basis for technology assessement - scientifically support SME's developments and demonstrations of innovative technologies - stimulate RTD for upgrading and development of new technologies - support professional training and education
T10.3a | Publication of papers in scientific journals, conferences and meetings | A10.3a | Creation of scientific publication review policy and structure | M9 |  |  | Scientific community, Universities, Research institutes, technical experts, government regulators | W-Smart
|  | D10.4 | Scientific publications | M12 | M12-M48 |  |  |  | (11) 8
T10.3b | Organisation of on-site conferences, workshops to present and benchmark main project results and outcomes | D10.5 | Presentations of project outcomes at scientific meetings | M24 | M24 - M48 |  |  |  | (10) 8
|  | A10.3b | Organization of on-site conferences and workshops for benchmarking project results | M24 | M24 - M48
T10.4 | Standardization support Objective : - Accelerate reliable integration of innovative SICT solutions in smart water network management
T10.4a | State of the art in smart-sensing and standardization | A10.4a | Benchmarking of best practices in smart-sensing and standardization | M12 | M12-M48 | End of each year | All stakeholders : industry, SMEs, utilities, government regulators, local governments, ISO & CEN experts, end-users and others | W-Smart | (0) 2
T10.4b | Certification of innovative technology | A10.4b | SICT certification for public works pre-qualification | To be determined
T10.4c | Promotion of Strategic partnerships with ISO, CEN, Certification commissions - using project outcome | A10.4c | Strategic collaborations with ISO and CEN for SICT functional standardization | To be determined
T10.5 | Reinforcement of industry competiveness
T10.5a | Promote the transfer of technology and innovations towards the industry and start-ups | A10.3b | SMEs’ Technology Transfer support and access to EU Demonstration Sites | M12 | M12-M48 |  | SME, local governments, regulators, utilities | W-Smart | (0) 2
T10.5b | Facilitate the industry access to demonstrators for training, development and verification of innovation technology | A10.3a | EU recognized Innovative Technology Verification and Training Facility | M12 | M12-M48
T10.5c | Organization of on-site workshops, demonstratiors visits | D-10.5 | Presentations at technological meetings : Presentations at scientific meetings will be prepared | M24 | M24 - M48 |  |  |  | (8)3*
|  | A10.3b | Organization of on-site conferences | M24 | M24 - M48
|  | A10.4d | Demonstration visits | M24 | M24 - M48
T10.5d | Publication of papers in technology and innovation oriented journals | D10.4 | Technological publications | M12 | M12-M48 |  |  |  | (8)2*
[8 empty] | Total | 53.7
Note* | In this Table for mutiple tasks using the same deliverable the Total Resources for this deliverable are indicated in person-months for the first task which yields this deliverable -no resources distribution is made to other tasks.
For any other subsequent tasks using the same deliverable the Total Resources for this deliverable are indicated for reference in parenthesis.
1 | Communication material | Tasks | T10.8 - development of dissemination tools, T10.6 - stakeholders' awareness building, T10.9 - internal communication
2 | Scientific and technical publications and press | Tasks | T10.3 - dissemination of scientific and innovation outcome, T10.5 - reinforcement of industry competiveness, T10.6 - stakeholders' awareness building
3 | Conference organizations, demo sites… | Tasks | T10.3 - dissemination of scientific and innovation outcome, T10.5 - reinforcement of industry competiveness, T10.6 - stakeholders' awareness building
4 | Intranet | Tasks | T10.8 - development of dissemination tools, T10.9 - internal communication
| Agenda | 1. D - Deliverable identified in the proposal
2. A- Additional Deliverables identified for specific tasks in the proposal
3. For Total Resources the original allocation of person-month for each deliverable indicated in the proposal is reported for reference in paranthesis

## SDP Framework 2
Task | Objectif | Deliverable | Description | Delivery Date | Period | Frequency | Target group | Lead partner | Total Ressources
T10.6 | Stakeholders' awareness building
T10.6a | Interaction with identified stakeholders, including financial sector, decision makers, regulators, utilities’ executives with communication to key persons; | D10.3 | Support materials: Newsletter, brochures, videos/movies, etc. | M3 | M3-M48 |  | All stakeholders : industry, SME, utilities, government regulators, local governments, ISO & CEN experts, end-users and others | W-Smart | (8)1*
T10.6b | Organization of manifestation, Exhibition and Demo-site Visit for end-users | A10.3b | On-site Demonstration Workshops for Target Stakeholders groups | M24 | M24-M48 | 2 per year |  |  | (8)3*
T10.6c | News coverage in national and local media (journals, TV, radio, etc,). | D10.4 | Dissemination through scientific publication, selected journals & magazines | M12 | M12-M48 |  |  |  | (8)2*
|  |  | Stakeholders’ Awareness Building through magazines, media (Com, TV, etc.) | M12 | M12-M48
T10.6d | Participation in stakeholders’ conferences on environmental challenges, innovation, etc. | A10.6c | Organization/Presentations in Stakeholders’ Conferences, Media programs, etc. | M24 | M24-M48 |  |  |  | (8)3*
T10.6e | Organization of meetings and workshops for local governments; |  |  | M24 | M24-M48
T10.7 | Contribution to FP7 Environment Objectives & Interaction with EIP
T10.7a | Synthetic Information Dissemination on the impact of main project achievements on meeting FP7 goals of industry boosting, social development and environment protection. | D10.6 | Dissemination activities for FP7 and EIP on Water focusing on: - communication of project results - stimulating applications of the project results - specifying R&D building forth | M12 | M12-M48 |  | European programs : FP7, EIP and others | Vitens | 3
T10.7b | At the beginning and at each reporting period: informational fact sheet, a short video targeting a wide public audience and a set of re-usable illustrations will be prepared | D10.7 D10.11 D10.12 D10.13 | Informational fact sheet, video and illustrations targeting a wide public audience at the beginning and at each reporting period | M1 |  | M1 M12 M30 M48 |  | Vitens | 2
T10.7c | Preparation of a policy brief at the end of the project; | D10.8 | Policy brief at the end of the project for Authorities and Regulators | M48 |  |  |  | Vitens | 2
T10.7d | Participation in the European Innovation Partnership (EIP) on Water by setting up an action group on smart water distribution networks. | A10.7 | Setting up a SWN Action Group for EIP collaboration. | M12 |  |  |  | Vitens
T10.7e | Participation in other action groups (e.g. City Blueprints, Finnowater); |  |  | M12
T10.7f | Activities to disseminate FP 7 related results: Dissemination activities will be carried out to present the project results to the actors in FP7 environment theme and EIP on water. | D10.9 | Project outcome Symposium | M48 |  |  |  | Vitens | (2,7) 2
T10.8 | To support long-life education programme on Smart Water Management
T10.8a | Creation of a pedagogic platform based on the demonstrator for undergraduate and post-graduate students | A10.8a | Academic Educational Platform and e-learning to spearhead SWN University Education | M24 | M24-M48 |  | Academic community, universities, students, research institutions | W-Smart | (0) 4
T10.8b | Development of dedicated courses in Smart Water Networks - education of future Water Systems Managers, Engineers and other related discipline Technical Experts | A10.8b | Multi-disciplinary UG and G Education courses and state-of-the-art programs | M24 | M24-M48
T10.8c | E-learning | A10.8c | E-learning platform | M36 | M36-M48
T10.8c | Organization of on-site - summer schools for MS and PhD students | A10.8d | On-site - Summer Schools for MS and PhD students | M24 | M24-M48
|  | A10.8e | Long Term Post-project Outcome Exploitation for Academic Education
T10.9 | Internal Communication from the individual WPs and demonstration sites to the consortium partners
T10.9a | Distribution of minutes of consortium meetings | D10.3 | Distribution of minutes of consortium meetings | M1 | M1-M48 |  | Partners | W-Smart | (8)1*
T10.9b | Secure intranet | D10.2 | Secure Intranet | M1 | M1-M48 |  |  | Vitens | (2)4*
T10.9c | Newsletters | D10.3 | Newsletters | M3 | M3-M48 |  |  | W-Smart | (8)1*
T10.10 | Strategic Partnerships for Leveraging Resources and Network Support
T10.10a | Exploring opportunities for mobilizing financial and other forms of support offered by national/regional authorities, private investments, other EU programs (e.g. structural funds, ) | A10.1 | Relationships with other EU funding mechanisms | M12 | M12-M48 |  | Eu program structural funds, EIP and other strategic partners to be identified | Vitens | 2.7
T10.10b | Meetings with relevant management authorities for the structural funds in the concerned region(s) at an early stage of the project for follow up on innovation and demonstration activities beyond the project. | A10.2 | Strategic Partnerships for Leveraging Resources, Networks, other Support | M18 | M18-M48 |  |  | Vitens
T10.10c | Exploring synergies with other EU funding mechanisms and establishing links/synergies with EU investment schemes | D10.10 | Overview of mobilized funding, relationships with organizations, synergies with other EU funding mechanisms | M24 |  | M24 M36 M48 |  | Vitens
T10.10d | Establishing relations with other EU funding mechanisms (European Regional Development Fund; Interreg; Horizon 2020) and exploring how SmartWater4Europe can contribute to these mechanisms (either by knowledge or participation);
T10.10e | Strategic Partnerships for Leveraging Networks, Resources, Financial and other Support
[8 empty] | Total | 53.7
Note* | In this Table for mutiple tasks using the same deliverable the Total Resources for this deliverable are indicated in person-months for the first task which yields this deliverable -no resources distribution is made to other tasks.
For any other subsequent tasks using the same deliverable the Total Resources for this deliverable are indicated for reference in parenthesis.
1 | Communication material | Tasks | T10.8 - development of dissemination tools, T10.6 - stakeholders' awareness building, T10.9 - internal communication
2 | Scientific and technical publications and press | Tasks | T10.3 - dissemination of scientific and innovation outcome, T10.5 - reinforcement of industry competiveness, T10.6 - stakeholders' awareness building
3 | Conference organizations, demo sites… | Tasks | T10.3 - dissemination of scientific and innovation outcome, T10.5 - reinforcement of industry competiveness, T10.6 - stakeholders' awareness building
4 | Intranet | Tasks | T10.8 - development of dissemination tools, T10.9 - internal communication
| Agenda | 1. D - Deliverable identified in the proposal
2. A- Additional Deliverables identified for specific tasks in the proposal
3. For Total Resources the original allocation of person-month for each deliverable indicated in the proposal is reported for reference in paranthesis

## Input Task 10.1
Task | Objectif | Deliverable | Description | Delivery Date | Period | Frequency | Target group | Lead partner | Total Ressources | Input requested from partners | Partner's Input & Comments
T.10.1 | Preparation of a dissemination strategy | A10.1 | SDP (Strategic Dissemination Plan) Framework including : | M6
T10.1a | Stakeholders' peer program review, impact assessment and depoyment recommendation | A10.1a | Stakeholders Board for benchmarking measures and impact assessment | M6 |  |  | Partners | W-Smart | (0) 2 | This task will be accomplished through SDP Planning & Coordination Meetings
T10.1b | Identification of the stakehorders' target groups at the local and European levels | A10.1b | Target Stakeholders’ groups | M6 | [5 empty] | Partners are both SDP owners and target stakeholders. Requested - Partner's input and comments on:
T10.1c | Determination of the action to be conducted relevant to each stakeholder's target group | A10.1c | Prioritized Actions For each target group at the project or partner levels | M9 | [5 empty] | 1. Partners' objectives and requirements for the SDP in the context of the EU Project Goals
T10.1d | Determination of the agenda of major actions | A10.1d | Action Plan and implementation procedure | M9 | [5 empty] | 2. Identified Target Stakeholders (recommendations for the Stakeholders' Board)
3. Prioritized Plan of Actions for Identified Stakeholders (Priority Rating Criteria ; synergies with corporate plan of actions)
4. Deliverables the partner expects to focus on (Rationale, objectives, information content, target stakeholders, expected impacts, synergies with Corporate tools)
5. Other task deliverables to be added as identified by the partners as approriate
6. Allocated Resources (Grant + Co-financing) by the partner for each devierable (person- monhs) - input for table SDP Ressources
7. Proprosed strageic Collaborations for leveraging resources and capabilities
8. SDP selected activities (objectives, identified stakeholders, expected impacts, timelines, resources, strategic partnerships, etc.)
9. Partner as the SDP Target Stakeholder - corporate requirements, deliverable use, expected information and impact assessment measures
10. Other issues identified by the partners
T10.1e | Reliable and Efficient DSP implemntation management | A10.1e | SDP Implementation - Organizational Management and quality control and updating | M9 | M9-M48 | Each 6M |  |  | (0) 2 | 1. SDP Implementation & Monitoring - Organizational Structure (recommendations)
2. implementation procedures (e.g information security terms, publication policy, IP, etc.)
3. SDP Implementation monitoring, quality control and impact benchamrking measures
4. SDP Updating

## Input Task 10.2
Task | Objectif | Deliverable | Description | Delivery Date | Period | Frequency | Target group | Lead partner | Total Ressources | Input requested from partners | Partner's Input & Comments
T10.2 | Development of dissemination tools and support Objective : - Support online and offline communication of project results and outcomes to target stakeholders | A10.2 | Communication and dissimation tools including : | M1 | M1-M48
T10.2a | Creation of the project graphic identity and communication chart | A10.2a | Communication chart and logo | M1 |  |  | Partners | W-Smart |  | On-Line and Off-line Communication Tools - Partners are both Tool Owners and Target Stakeholders. Requested - Partner's input and comments on:
T.10.2b | Online Communication : Creation of a web-site, blog, newsletter, electronic diffusion lists | D10.1 | Website : Website with project information, project progress information and services | M1 | M1-M48 |  | All stakeholders | W-Smart | 4 | 1. Partners' expectations and requirements for communication tools - prioritization
2. Online and offline tools the partner expects to focus on (Rationale, objectives, information content, target stakeholders, expected impacts, synergies with Corporate tools)
|  | D10.2 | Intranet | M1 | M1-M48 |  | Partners | Vitens | (3) 2 | 3. Recommendations and requirements for upgrading the website and the extranet
|  | D10.3 | Newsletters and other online communication material | M3 | M3-M48 | Each 3 month | Partners and target stakeholders | W-Smart | (14) 8 | - Additional benefits the website/extranet could bring you
T.10.2c | Offline Communication : Creation of printed support for the project (flyer, brochure, booklet) | A10.2b | Offline communication material (flyer, brochure, booklet) | M9 | M9-M48 |  | Depending on target objective | W-Smart |  | - Information or services you would like to find that you don't have yet?
T10.2d | Creation of videos/movies on the project challenges and main achievements | A10.2c | Video material | M9 | M9-M48 | M9 ; M24 M36 ; M48 | Depending on target objective | W-Smart |  | - Information or services you would like to provide which require redesign
T10.2e | Communication tools to meet partners' needs and requirements | A10.2d | Other communication material will be prepared upon partners' input | To be determined |  |  | Depending on target objective | W-Smart |  | - Addtional pages/functionalities for the website design architecture
4. Continuous website updating and information feeding issues as identified by the Partner
5. Partners' requirements and recommandations for upgrading the newsletter and other communication tools
6. Partner and Target Stakeholder - corporate requirements, tool use, expected information and impact assessment measures
7. Allocated Resources (Grant + Co-financing) by the partner for selected tools (person- months) - input for table SDP Ressources
8. Tools depolyment procedures (e.g information security terms, liabilities, etc.)
9. Tools deployment monitoring, quality control and impact benchamrking measures
10. Continuous Tools Upgrading Recommendations

## SDP Ressources
Task | Deliverable | Description | Delivery Date | Lead partner | Total Ressources | Vitens | Acciona Agua | TWUL | USTL | Intellect Water | Optisense | Syrinix | CEA | S::can | Vernon morris and co | Quasset | Calm Water | KWR | Citic Eurarfid | Arson Technology | USFD | Homeria | Mycometer | W-Smart | Stereograph | Solvd
[6 empty] | 6.00 | 7.00 | 5.00 | 2.50 | 2.70 | 2.00 | 0.70 | 1.00 | 2.00 | 1.00 | 2.00 | 4.00 | 2.00 | 1.00 | 1.20 | 1.60 | 2.00 | 1.00 | 6.00 | 3.00
T.10.1 | A10.1 | Preparation of a dissemination strategy | M6
SDP (Strategic Dissemination Plan) Framework including :
| A10.1a | Stakeholders Board for benchmarking measures and impact assessment | M6 | W-Smart | (0) 2
| A10.1b | Target Stakeholders’ groups | M6
| A10.1c | Prioritized Actions For each target group at the project or partner levels | M9
| A10.1d | Action Plan and implementation procedure | M9
| A10.1e | SDP Implementation - Organizational Management and quality control and updating | M9 |  | (0) 2
T10.2 | A10.2 | Development of dissemination tools and support Objective : - Support online and offline communication of project results and outcomes to target stakeholders | M1
| A10.2a | Communication chart and logo | M1 | W-Smart
| D10.1 | Website : Website with project information, project progress information and services | M1 | W-Smart | 4
| D10.2 | Intranet | M1 | Vitens | (3) 2
| D10.3 | Newsletters and other online communication material | M3 | W-Smart | (14) 8
| A10.2b | Offline communication material (flyer, brochure, booklet) | M9 | W-Smart
| A10.2c | Video material | M9 | W-Smart
| A10.2d | Other communication material will be prepared upon partners' input | To be determined | W-Smart
T10.3 |  | Dissemination of scientific and innovation outcomes Objectives : - provide scientific basis for technology assessement - scientifically support SME's developments and demonstrations of innovative technologies - stimulate RTD for upgrading and development of new technologies - support professional training and education
| A10.3a | Creation of scientific publication review policy and structure | M9 | W-Smart
| D10.4 | Scientific publications | M12 |  | (11) 8
| D10.5 | Presentations of project outcomes at scientific meetings | M24 |  | (10) 8
| A10.3b | Organization of on-site conferences and workshops for benchmarking project results | M24
T10.4 |  | Standardization support Objective : - Accelerate reliable integration of innovative SICT solutions in smart water network management
| A10.4a | Benchmarking of best practices in smart-sensing and standardization | M12 | W-Smart | (0) 2
| A10.4b | SICT certification for public works pre-qualification | To be determined
| A10.4c | Strategic collaborations with ISO and CEN for SICT functional standardization | To be determined
T10.5 |  | Reinforcement of industry competiveness
| A10.3b | SMEs’ Technology Transfer support and access to EU Demonstration Sites | M12 | W-Smart | (0) 2
| A10.3a | EU recognized Innovative Technology Verification and Training Facility | M12
| D-10.5 | Presentations at technological meetings | M24 |  | (8)3*
| A10.3b | Organization of on-site conferences | M24
| A10.4d | Demonstration visits | M24
| D10.4 | Technological publications | M12 |  | (8)2*
T10.6 |  | Stakeholders' awareness building
| D10.3 | Support materials: Newsletter, brochures, videos/movies, etc. | M3 | W-Smart | (8)1*
| A10.3b | On-site Demonstration Workshops for Target Stakeholders groups | M24 |  | (8)3*
| D10.4 | Dissemination through scientific publication, selected journals & magazines | M12 |  | (8)2*
|  | Stakeholders’ Awareness Building through magazines, media (Com, TV, etc.) | M12
| A10.6c | Organization/Presentations in Stakeholders’ Conferences, Media programs, etc. | M24 |  | (8)3*
M24
T10.7 |  | Contribution to FP7 Environment Objectives & Interaction with EIP
| D10.6 | Dissemination activities for FP7 and EIP on Water focusing on: - communication of project results - stimulating applications of the project results - specifying R&D building forth | M12 | Vitens | 3
| D10.7 D10.11 D10.12 D10.13 | Informational fact sheet, video and illustrations targeting a wide public audience at the beginning and at each reporting period | M1 | Vitens | 2
| D10.8 | Policy brief at the end of the project for Authorities and Regulators | M48 | Vitens | 2
| A10.7 | Setting up a SWN Action Group for EIP collaboration. | M12 | Vitens
M12
| D10.9 | Project outcome Symposium | M48 | Vitens | (2,7) 2
T10.8 |  | To support long-life education programme on Smart Water Management
| A10.8a | Academic Educational Platform and e-learning to spearhead SWN University Education | M24 | W-Smart | (0) 4
| A10.8b | Multi-disciplinary UG and G Education courses and state-of-the-art programs | M24
| A10.8c | E-learning platform | M36
| A10.8d | On-site - Summer Schools for MS and PhD students | M24
| A10.8e | Long Term Post-project Outcome Exploitation for Academic Education
T10.9 |  | Internal Communication from the individual WPs and demonstration sites to the consortium partners
| D10.3 | Distribution of minutes of consortium meetings | M1 | W-Smart | (8)1*
| D10.2 | Secure Intranet | M1 | Vitens | (2)4*
| D10.3 | Newsletters | M3 | W-Smart | (8)1*
T10.10 |  | Strategic Partnerships for Leveraging Resources and Network Support
| A10.1 | Relationships with other EU funding mechanisms | M12 | Vitens | (2) 2,7
| A10.2 | Strategic Partnerships for Leveraging Resources, Networks, other Support | M18 | Vitens
| D10.10 | Overview of mobilized funding, relationships with organizations, synergies with other EU funding mechanisms | M24 | Vitens
|  |  |  | Total | 53.7 | 6.00 | 7.00 | 5.00 | 2.50 | 2.70 | 2.00 | 0.70 | 1.00 | 2.00 | 1.00 | 2.00 | 4.00 | 2.00 | 1.00 | 1.20 | 1.60 | 2.00 | 1.00 | 6.00 | 3.00
Note* | In this Table for mutiple tasks using the same deliverable the Total Resources for this deliverable are indicated in person-months for the first task which yields this deliverable -no resources distribution is made to other tasks.
For any other subsequent tasks using the same deliverable the Total Resources for this deliverable are indicated for reference in parenthesis.
| 1 | Communication material | Tasks: | T10.8 - development of dissemination tools, T10.6 - stakeholders' awareness building, T10.9 - internal communication
| 2 | Scientific and technical publications and press | Tasks: | T10.3 - dissemination of scientific and innovation outcome, T10.5 - reinforcement of industry competiveness, T10.6 - stakeholders' awareness building
| 3 | Conference organizations, demo sites… | Tasks: | T10.3 - dissemination of scientific and innovation outcome, T10.5 - reinforcement of industry competiveness, T10.6 - stakeholders' awareness building
| 4 | Intranet | Tasks: | T10.8 - development of dissemination tools, T10.9 - internal communication
|  | Agenda | 1. D - Deliverable identified in the proposal
2. A- Additional Deliverables identified for specific tasks in the proposal
3. For Total Resources the original allocation of person-month for each deliverable indicated in the proposal is reported for reference in paranthesis

## Timeline
Delivery number | Deliverable | Total ressources person-months | Duration months | Starting date | Finish date | Ressource % all partners | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28 | M29 | M30 | M31 | M32 | M33 | M34 | M35 | M36 | M37 | M38 | M39 | M40 | M41 | M42 | M43 | M44 | M45 | M46 | M47 | M48
A10.1 (A10.1a - A10.1b - A10.1c - A10.1d) | SDP (Strategic Dissemination Plan) Framework | 2 | 9 | 2014-01-01 08:00 | 2014-09-30 17:00 | 22%
A10.1e | Organizational management and quality control updating | 2 | 39 | 2014-10-01 08:00 | 2017-12-29 17:00 | 5%
D10.1 | Creation of website | 1 | 1 | 2014-01-01 08:00 | 2014-01-31 17:00 | 100%
D10.1 | Website maintenance | 3 | 47 | 2014-02-03 08:00 | 2017-12-29 17:00 | 6%
D10.2 | Intranet | 1 | 1 | 2014-01-01 08:00 | 2014-01-31 17:00 | 100%
D10.2 | Intranet maintenance | 1 | 47 | 2014-02-03 08:00 | 2017-12-29 17:00 | 2%
D10.3 | Newsletter | 2 | 45 | 2014-03-27 | 2017-12-29 17:00 | 100%
D10.3 (A10.2b - A10.2c - A10.2d) | Communication material | 6 | 44 | 2014-04-30 08:00 | 2017-12-29 17:00 | 14%
D10.4 | Press + Scientific and technical publications | 8 | 36 | 2015-01-01 08:00 | 2017-12-29 17:00 | 22%
D10.5 - A10.3b - A10.6c | Presentation and organization of on-site conferences, workshops, meetings | 8 | 24 | 2016-01-01 08:00 | 2017-12-29 17:00 | 33%
A10.4a - A10.4b - A10.4c | Standardization support | 2 | 36 | 2015-01-01 08:00 | 2017-12-29 17:00 | 5%
A10.3b - A10.3a | SMEs' Technology Transfer support | 2 | 36 | 2015-01-01 08:00 | 2017-12-29 17:00 | 5%
D10.6 | Dissemination activities for FP7 and EIP on Water | 3 | 36 | 2015-01-01 08:00 | 2017-12-29 17:00 | 8%
D10.7 | Year 1 : Information fact sheet, video and illustrations | 0.5 | 1 | 2014-12-01 08:00 | 2014-12-31 17:00 | 50%
D10.11 | Year 2 : Information fact sheet, video and illustrations | 0.5 | 1 | 2015-12-01 08:00 | 2015-12-31 17:00 | 50%
D10.12 | Year 3 : Information fact sheet, video and illustrations | 0.5 | 1 | 2016-11-30 08:00 | 2016-12-30 17:00 | 50%
D10.13 | Year 4 : Information fact sheet, video and illustrations | 0.5 | 1 | 2017-11-29 08:00 | 2017-12-29 17:00 | 50%
D10.8 | Policy brief for Authorities and Regulators | 2 | 4 | 2017-09-11 08:00 | 2017-12-29 17:00 | 50%
D10.9 | Project outcome Symposium | 2 | 4 | 2017-09-11 08:00 | 2017-12-29 17:00 | 50%
A10.8a - A10.8b - A10.8c - A10.8d - A10.8e | Support long-life education program on Smart Water Management | 4 | 36 | 2015-01-01 08:00 | 2017-12-29 17:00 | 11%
A10.1 - A10.2 - D10.10 | Strategic Partnerships for leveraging Resources and Network Support | 2.7 | 36 | 2015-01-01 | 2017-12-29 | 8%
To make this Diagram, we used Microsoft Project 2013. Microsoft Office Project offers tools for more efficient project management. Microsoft Project can be used in a variety of industries including construction, manufacturing, pharmaceuticals, government, retail, financial services and health care. The main modules of Microsoft Project include project work and project teams, schedules and finances. Microsoft Project allows its users to set realistic goals for project teams and customers by creating schedules, distributing resources and managing budgets. Finally, Microsoft Project comes with customizable wizard that walks users through the process of project creation, from assigning their tasks and resources to reporting the final result
Total ressources = number of person-month
Total duration months = period during which we will work on this task in number of months
Starting date = The date when we start working on the task
Finish date = delivery date
Ressources % = total ressources / total duration (%)